Gokul Ramachandran
Jeff Heckey

ECE 253 Project: Tetris

Project Plan
1. VGA display output (Wed 11/13)
  1. Get VGA pcore instantiated and able to output to a screen
  2. Instantiate all support modules (RAMs, etc.)
2. Control display (Sat 11/16)
  1. Change colors automatically from the program
  2. -OR- display text
  3. Change periodically
3. Get inputs (Sun 11/17)
  1. React to interrupts from rotary encoder by changing LEDs
4. Use inputs to control display (Tue 11/19)
  1. Change the colors/text on the display on input
5. Draw a static scene (Thu 11/21)
  1. Demonstrate non-uniform output from VGA controller
  2. Multiple values in VRAM
6. Draw a moving object (Fri 11/22)
  1. Use MicroBlaze to dynamically draw a moving object (pong ball)
  2. Demonstrate clean refresh
7. Control a moving object with inputs (Sun 11/24)
  1. Use interrupts to move an object on the screen
  2. Demonstrate control of VRAM
  3. Demonstrate clean refresh
8. Draw game board and pieces (Tue 11/26)
  1. Implement data structures and basic units for Tetris
9. Make tetramino fall (Fri 11/29)
  1. Integrate movement with game board and non-uniform shapes
  2. Stop block at the right elevation
  3. Show control over display and object motion
10. Make tetramino move (Sat 11/30)
  1. Integrate the controls into main loop
  2. Update the movement without tearing
  3. Stop the tetramino at the right elevation
11. Make tetramino rotate (Sun 12/1)
  1. Flip it without poor updating
12. Color pieces (Tue 12/3)
  1. Oooh! Pretty!
13. Clear lines (Thu 12/5)
  1. Detect complete line(s)
  2. Large screen update (drop floating blocks)
14. Add scoring (Sat 12/7)
  1. Calculate and track score
  2. Display next to screen

Plan B and C:
(After step 7)
1. Pong! (+3 days)
  1. Draw paddle
  2. Automatic object (ball) reacts with paddle location
  3. Angle adjusts depending on ball offset on paddle
2. Breakout (Pong+3 days)
  1. Draw bricks
  2. Destroy bricks on ball impact (collision detection)
  3. Update ball direction based on impact

Log:
11/11:
Reviewed VGA implementation options
Established initial dev plan
Set basic, stretch and backup goals
Read lots of documentation

11/13:
Got VGA output! Red checker board
Discussed various VGA output merits – TFT pcore vs homebrew
Decided on homebrew
Pros:
Less need for video RAM
Better control of sprites, data flow, and interrupts
Con:
PLB interface/custom pcore build could be challenging to build, debug

11/15:
Got VGA driver timed better
Generated the scanline BRAM and wrote the FIFO wrapper

11/17:
Went with pcore model
Modified VGA driver to take in 16 pixels at a time (glyph width)

11/19:
Got the VGA driver to work with 16 pixel width
Wrote a basic tb to test it and get that working. Allows for tiled displays
Behind on schedule, need to get VGA integrated into pcore and attached to PLB bus

11/20:
Found a good tutorial for how to create a PCore. Generated an initial pass. Not quite right, but no easy way to correct it other than regenerating.

11/21:
Got an XPS project complete an merged into SDK for this. The VGA is integrated into the Pcore. It doesn't appear to be working at this point – we have no VGA output, but the software appears to be running. A few possibilities include observing the VGA pins to see if they are working as in the standalone mode (drive strength settings were not ported because of unclear mapping from “Slow” to “2|4|8|10|12|16” values, or some such), running an internal test, verifying pin mappings.
Also reduced the memory footprint to 16K as a precaution, but the C projects are BIG! Might need to go back to 32K, but I can't find an easy way to shift that. Will take a new XPS project I think.

11/22:
Reworked the VGA to be big endian to match the Pcore and reduce some of the potential source of error. Unfortunately, this completely destroyed the output.

11/25:
Got VGA back, but I am noticing a lot more marginality with the pixels. About 60 columns (30 columns 2 pix wide) are fuzzy. I'm guessing this has some timing issues, but I'm not sure why I wasn't seeing this before. The issue definitely is with two pixels repeatedly swapping places (or being drawn longer/shorter on some frames than others). I can adjust the slew rate and drive strength, which should at least have a noticeable effect on the issue if it is analog, but not if it is logical. That said, I'm far enough behind that I should try to get it integrated into the Pcore rather than futzing with it more until the project has progressed further.
Additional note: Gokul has stated a desire to drop the class and leave the project. He will need the time to interview for a job and since this class is not a requirement for his graduation, the prudent choice seems to be to let him go.

11/28:
Found the source of the display disappearing: I still had the clear and enable bits mapped as little-endian instead of big. Fixed that problem. Laid out an initial rendering algorithm naively, and fan-in was too high. Took a long time to get all of the parameters in place so that burned most of my day until Thanksgiving dinner.

11/29:
Rewrote rasterization engine to be more pipelined to deal with the fan-in. Got the gameboard rendering. Can update the board very rapidly, so refresh should not be an issue. :) Today was a good day.

11/30:
Got timer interrupt working – found that the interrupts were incorrectly connected to Microblaze. I had to debug through all of the FW libraries and back into the XPS configuration to find the issue. I then had hack the MHS from my project with some changes from Lab 1.
Got the VGA interrupts working. Again, dug through everything from hardware to software and read through the interrupt controller doc for custom IP. Figured out a lot about the interrupts. Digging through the VHDL top-level, though, I found that the INTR registers were offset differently than in the drivers. It looked like when I regenerated the VGA core I changed an option and so the interrupts moved from 0x100 to 0x200, but the drivers were not regenerated, so the defines had 0x100. Fixing that got them working.
Took some measurements: time to redraw entire gameboard is ~3000 cycles (enable timer, loop over address range, update value to write (3 ops), ) or around 0.05 ms. Leaves me plenty of time for other things.